Project: Pixel Pulse. – Launch of a digital magazine dedicated to retro gaming and hardware preservation.

Main Objective: To publish the inaugural 50-page digital issue and launch the accompanying web platform with a searchable hardware database.

| Major Task | Specific Actionable Subtasks |
| --- | --- |
| 1. Content & Strategy | 1.1 Finalize editorial calendar and "State of the Industry" report. 1.2 Research and input image gallery and specs for the hardware database. |
| 2. Front-End Development | 2.1 Develop responsive UI components for the digital reader. 2.2 Build interactive "Hardware Database" tool frontend. |
| 3. Back-End Development | 3.1 Architect the relational database schema for hardware specs. 3.2 Develop the REST API for content retrieval. |
| 4. Full-Stack & DevOps | 4.1 Integrate Stripe API for secure subscription payments. 4.2 Configure CI/CD pipeline and cloud hosting environment. |
| 5. Testing & Launch | 5.1 Perform cross-browser compatibility and mobile responsiveness testing. 5.2 Execute final security audit and penetration test on user data. |

Step 2: Identify Roles

Editor-in-Chief (Ellie): Approves final content strategy and product roadmap.

Content Writer (Charlie): Produces articles and maintains the accuracy of the technical database entries.

Front-End Developer (Sally): Focuses on the user interface, CSS architecture, and client-side performance.

Back-End Developer (Lucy): Manages the database, server logic, and API endpoints.

DevOps/Full-Stack Engineer (Snoopy): Handles infrastructure, security, payment integrations, and deployment.

| Tasks / Roles | Ellie (EIC) | Charlie (Writer) | Sally (Front-End) | Lucy (Back-End) | Snoopy (DevOps) |
| --- | --- | --- | --- | --- | --- |
| 1.1 Cover Story | A | R | I | I | I |
| 1.2 Import Gallery | I | R | C | A | I |
| 2.1 Responsive UI | C | I | R | C | A |
| 2.2 Database | I | C | R | R | I |
| 3.1 Database Schema | I | C | I | R | A |
| 3.2 Content API | A | I | C | R | I |
| 4.1 Payment Integration | A | I | C | C | R |
| 4.2 Cloud Hosting | I | I | I | C | R |
| 5.1 Browser Testing | C | I | R | A | I |
| 5.2 Security Audit | A | I | I | C | R |

To Implement into Confluence

Create new Table by clicking “insert’ then “Table”

Build Structure of 11 rows and 6 columns (Making sure to have those extra collums for headers )

Used Fixed with for mobile friendly

Use Status Macro with color coating for RACI